## Slide 1: GREEN WORLD –HAPPY PEOPLE
ERASMUS+ KA2 PROJECT

## Slide 2: MEETING CONTENT
DISSEMINATION /15.00 -15.30 /
PROJECT ACTIVITIES FOR THE FIRST YEAR /15.30 – 16.00/
BUDJET /16.OO -16.30 /
QUESTIONS /16.30 – 17.00/

## Slide 3: DISSEMINATION
PROJECT SITE
PROJECT FACEBOOK PAGE
eTwinning
LOCAL PAPERS AND MEDIAS

## Slide 4: ACTIVITIES BY THE END OF NOVEMBER FOR THE PROJECT SITE I NEED
INFORMATION ABOUT YOUR SCHOOLS
PHOTOES OF YOUR SCHOOLS
PICTURE FROM SOME BEAUTIFUL SIGHT OF NATURE FROM YOUR COUNTRY
LINK TO A SITE OR A SUBPAGE WHERE YOU ARE GOING TO SHARE PROJECT RESULTS

## Slide 5: ACTIVITIES BY THE END OF NOVEMBER
PROJECT SITE NAD FACEBOOK PAGE 
eTwinning PROJECT 
LOGO
MASCOT
EXCHANGE OF VIDEOS AND PRESENTATIONS ABOUT PARTICIPATING SCHOOLS

## Slide 6: ACTIVITIES BY THE END OF DECEMBER
PROJECT CORNER AT EACH SCHOOL
ECO-CALENDAR
PHOTO CONTEST
EXCHANGE OF NEW YEAR’S GREETING CARDS

## Slide 7: ACTIVITIES BY THE END OF FEBRUARY
Designing Code of Ecologist
Interview with local authorities and companies about their environmental impact
Making a movie HOW WE LOOK AFTER THE NATURE

## Slide 8: ACTIVITIES BY THE END OF APRIL
FIRST LEARNING TEACHING TRAINING ACTIVITY IN PORTUGAL
TOPIC OF THE ACTIVITY “CLIL LESSONS DEDICATED TO THE ENVIRONMENT”

## Slide 9: ACTIVITIES BY THE END OF APRIL
Workshop with representatives from local recycling companies dedicated to the GLOBAL RECYCLING DAY
Organizing a workshop for making objects from recycled materials

## Slide 10: ACTIVITIES BY THE END OF APRIL
Planting trees campaign dedicated to the INTERNATIONAL DAY OF FORESTS
Composing Song of Environment dedicated to the INTERNATIONAL DAY OF EARTH
Attending Ecology and Environment conference / by students from the Bulgarian school to present the achieved project impact during the first year/

## Slide 11: ACTIVITIES BY THE END OF JUNE
Designing "what we have learnt" diaries between partners and exchanging them
Video-conference on "what we have learnt about ecology“
Concert to promote environmental awareness

## Slide 12: BUDGET
PAYMENTS
FIRST PAYMENT /ALREADY DONE/ - 40 % OF THE BUDGET
SECOND PAYMENT /DUE TO SEPTEMBER 2021/ - 40 % OF THE BUDGET
THIRD PAYMENT /AFTER THE BALANCE PAYMENT BY THE NATIONAL AGENCY OF BULGARIA/ - 20 % OF THE BUDGET

## Slide 13: BUDGET
PROJECT MANAGEMENT
TRANSNATIONAL MEETING /TWO MEETINGS/
LEARNING TEACHING TRAINING ACTIVITIES /FOUR/

## Slide 14: PROJECT MANAGEMENT
3 OOO EUROES PER YEAR OR
THE TOTAL OF 6 OOO EUROES FOR THE PROJECT IMPLEMENTATION
THESE ARE MONEY FOR THE IMPLEMENTATION OF THE PROJECT ACTIVITIES

## Slide 15: PROJECT MANAGEMENT
YOU DO NOT NEED TO SEND TO THE COORDINATOR ANY PROOFS
YOU NEED TO KEEP RECORD OF ALL THE DOCUMENTS THAT PROVE THE WAY YOU SPEND THIS MONEY

## Slide 16: TRANSNATIONAL MEETINGS
FIRST TRANSNATIONAL MEETING –WITHIN THE FIRST YEAR OF THE PROJECT IMPLEMENTATION IN LITHUANIA
SECOND TRANSNATIONAL MEETING – AT THE END OF THE PROJECT IMPLEMENTATION, BY SEPTEMBER 2022

## Slide 17: TRANSNATIONAL MEETINGS TRAVEL AND INDIVIDUAL SUPPORT
 | POLAND | PORTUGAL | LITHUANIA | TURKEY | ROMANIA
FIRST MEETING | 575 | 760 | - | 575 | 575
SECOND MEETING | 575 | 760 | 575 | - | 575
TOTAL | 1150 | 1520 | 575 | 575 | 1150

## Slide 18: VIRTUAL TRANSNATIONAL MEETINGS IN CASE OF COVID-19
No additional unit costs are eligible for virtual activities. The resources available under the “Project management and implementation” budget shall cover the costs related with these meetings.

## Slide 19: LEARNING TRAINING TEACHING ACTIVITIES
FIRST LTT – IN PORTUGAL /APRIL 2021
SECOND MEETING – IN BULGARIA /SEPTEMBER 2021
THIRD MEETING – IN ROMANIA /MARCH -APRIL 2022
FOURTH MEETING – IN POLAND /MAY-JUNE 2022

## Slide 20: LEARNING TEACHING TRAINING ACTIVITIES TRAVEL AND INDIVIDUAL SUPPORT
 | POLAND | PORTUGAL | LITHUANIA | TURKEY | ROMANIA
FIRST LTT | 5030 | - | 5030 | 5030 | 5030
SECOND LTT | 4435 | 5030 | 4435 | 4435 | 3770
THIRD LTT | 4435 | 5030 | 4435 | 3770 | -
FOURTH LTT | - | 5030 | 3770 | 4435 | 4435
TOTAL | 13900 | 15090 | 17670 | 17670 | 13235

## Slide 21: VIRTUAL LEARNING TEACHING TRAINING ACTIVITIES IN CASE OF COVID-19
No grant support for travel will be awarded.
Individual support: the grant amount is calculated by multiplying the number of days of virtual participation per participant, by 15% of the unit contribution applicable per day/month for the type of participant and for the receiving country concerned, as specified in Annex IV of the Agreement. Travel days before or after the activity cannot be included for the calculation of the individual support.

## Slide 22: VIRTUAL LEARNING TEACHING TRAINING ACTIVITIES IN CASE OF COVID-19
 | POLAND | PORTUGAL | LITHUANIA | TURKEY | ROMANIA
FIRST LTT | 376,50 | - | 376,50 | 376,50 | 376,50
SECOND LTT | 376,50 | 376,50 | 376,50 | 376,50 | 376,50
THIRD LTT | 376,50 | 376,50 | 376,50 | 376,50 | -
FOURTH LTT | - | 376,50 | 376,50 | 376,50 | 376,50
TOTAL | 1129,50 | 1129,50 | 1506 | 1506 | 1129,50

## Slide 23: VIRTUAL LEARNING TEACHING TRAINING ACTIVITIES IN CASE OF COVID-19
IN CASE OF VIRTUAL TRANSNATIONAL MEETINGS AND VIRTUAL LEARNING TECHING TRAINING ACTIVITIES AN ANNEX TO THE PARTNERS AGREEMENT WILL BE SIGNED

## Slide 24: BUDGET TRANSFERS
 | MANAGEMENT | TRANSNATIONAL MEETINGS | LTTs
UP TO 20 % | TO TRANSNATIONAL MEETING OR TO LEARNING TRAINING TEACHING ACTIVITIES | TO LEARNING TEACHING TRAINING ACTIVITIES | TO TRANSNATIONAL MEETINGS
YOU ARE NOT ALLOWED TO TRANSFER MONEY TO MANAGEMNT

## Slide 25: THANK YOU FOR YOUR ATTENTION

## Slide 26: GREEN WORLD –HAPPY PEOPLE
ERASMUS+ KA2 PROJECT